## Example
Project Name | Book Catalogue
Project Description | An application to catalogue the books the user has read; incorporates databases, a GUI, and hopefully AI.
Modules | Milestone | Due Date | Goal % Complete | Actual % Complete | What is the test? | Expected results of test | Actual results of test | January 15th
I. Main Database | 1. Install & configure MySQL | Friday, January 15th, 2021 | 100% | 100% | Can I use the MySQL client to create a database, create tables, and query those tables using SQL? | Yes, I should be able to. | Yes, I was able to start the MySQL server and connect with the client to create a database, tables, and was able to query the tables. | January 22nd
| 2. Install & configure Hibernate | Friday, January 15th, 2021 | 100% | 100% | Will a sample program that uses Hibernate to access the database compile? | Yes, the program should compile. | I had some trouble with this one. When my program finally compiled, I later learned that compilation wasn't a good enough test, as Hibernate didn't run. However, as detailed in my journal, I fixed the issue and Hibernate now runs. | January 29th
| 3. Write and annotate the Book class | Friday, January 22nd, 2021 | 100% | 100% | Can I use Hibernate with the Book class to perform CRUD operations in the database (and see the changes with the MySQL console)? | Yes, I should see the results from the operations in the database with the MySQL console. | Yes, I was able to see the results of the CRUD operations on Books in the database using the MySQL console. | February 5th
| 4. Write and annotate the Tag class | Friday, January 22nd, 2021 | 100% | 100% | Can I use Hibernate with the Tag class to perform CRUD operations in the database (and see the changes with the MySQL console)? | Yes, I should see the results from the operations in the database with the MySQL console. | Yes, I was able to see the results of the CRUD operations on Tags in the database using the MySQL console. | February 12th
| 5. Provide a function to add a book with tags | Friday, January 29th, 2021 | 100% | 100% | After calling this function, do I see the resulting tags and book entries in the database through the MySQL console? | Yes, I should see the new tag and book entries through the MySQL console. | Yes, I was able to see the new book entry and the new tag entries using the MySQL console. | February 19th
| 6. Create a class to represent a query based on tags & built-in book properties | Friday, January 29th, 2021 | 50% | 65% |  |  |  | February 26th
|  | Friday, February 5th, 2021 | 100% | 100% | Does the class correctly represent a query to find all of the books that are science fiction and tagged with 'good', 'great', or 'awesome', but not those also tagged with 'romance'? | Yes, the class should correctly represent that query. | Yes, the class did represent that query correctly.
| 7. Provide a function to search for books given a query | Friday, February 12th, 2021 | 100% | 100% | Does this function form the correct SQL, as outputted by Hibernate, that matches the custom query input? | Yes, the function should form the correct SQL. | Yes, the function formed the correct SQL (Hibernate outputs the generated SQL on demand). It also returned the correct subset of books from the database that matched the query. | March 5th
| 8. Provide a function to remove all books that match a query | Friday, February 12th, 2021 | 100% | 100% | After calling this function, do I see that the matching books were removed in the database through the MySQL console? | Yes, I should see the absence of matching books through the MySQL console. | Yes, I did see the presence of the matching books before the remove function was called and the absence of the matching books after the function was called. | March 12th
| 9. Provide a function to update multiple properties/tags of one book | Friday, February 19th, 2021 | 100% | 100% | After calling this function, do I see that the matching book was updated with the new properties and tags in the database through the MySQL console? | Yes, I should see that the matching book was updated with the new properties and tags in the MySQL console. | Yes, I did see that the matching book was updated with the new properties and tags in the MySQL console. | March 19th | (spring break)
| 10. Ensure that the program handles the starting and stopping of the MySQL daemon itself* | Friday, February 19th, 2021 | 100% | 100% | Does calling the start function actually start the MySQL daemon? Does calling the stop function actually stop the MySQL daemon? | In Task Manager, the mysqld program should appear when the start function is called. When the stop function is called, the mysqld program should disappear from Task Manager. | The mysqld program did appear when the start function was called, and when the stop function was called, the mysqld program did disappear. | March 26th
II. GUI | 1. Create the book insertion GUI layout | Friday, February 26th, 2021 | 100% | 100% | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | April 1st (Thurs) or April 5th (Mon) | april 2 is holiday
| 2. Link the book insertion GUI with the backend | Friday, February 26th, 2021 | 100% | 100% | After inserting a book through the GUI, do I see the resulting new book and tag entries in the database through the MySQL console? | Yes, I should see the resulting new book and tag entries through the MySQL console. | I did the see the resulting entries through the MySQL console. | April 9th
| 3. Create the book search GUI layout | Friday, March 5th, 2021 | 100% | 100% | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | April 16th
| 4. Link the book search GUI with the backend | Friday, March 12th, 2021 | 100% | 100% | Does the GUI display the same results as the backend does for the query to find all of the books that are science fiction and tagged with 'good', 'great', or 'awesome', but not those also tagged with 'romance'? | Yes, the GUI should display the same results as the backend. | Yes, the GUI did display the same results as the backend. | April 23rd
| 5. Create the book view GUI layout | Friday, March 12th, 2021 | 100% | 100% | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | April 29th (Thurs) or May 3rd (Mon) | april 30 is holiday
| 6. Create the book update GUI layout | Friday, March 26th, 2021 | 100% | 100% | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | May 7th
| 7. Link the book view and update GUIs together, and with the backend | Friday, March 26th, 2021 | 100% | 100% | Does pressing the 'update' button/tab on the view GUI call/change into the update GUI? After an update, do I see that the book was updated with the new properties and tags in the database through the MySQL console? | Yes, the GUI should change into the update GUI upon the pressing of the 'update' button/tab. Yes, I should see that the corresponding book was updated through the MySQL console. | Yes, the GUI does change into the update GUI upon the pressing of the 'update' button/tab. Yes, I do see that the corresponding book was updated through the MySQL console. | May 14th
| 8. Link the book view and update GUIs with the book search GUI | Friday, March 26th, 2021 | 100% | 100% | Does pressing the 'view' button on a search result in the book search GUI bring us to the view GUI? Does pressing the 'update' button on a search result in the book search GUI bring us to the update GUI? | Yes, pressing the 'view' button on a search result should bring us to the view GUI. Pressing the 'update' button on a search result should bring us to the update GUI. | Yes, pressing the 'view' button on a search result does bring us to the view GUI. Pressing the 'update' button on a search result does bring us to the update GUI.
| 9. Create the home GUI layout | Monday, April 5th, 2021 | 100% | 100% | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | N/A (as the layout/design can't really be incorrect) | May 21th | (note that 21 is graduation)
| 10. Link the home GUI with the other GUIs | Monday, April 5th, 2021 | 100% | 100% | Does pressing the 'insert' or 'search' buttons take you to the appropriate GUI? | Yes, pressing the 'insert' button should take you to the insert GUI and pressing the 'search' button should take you to the search GUI. | Yes, pressing the 'insert' button does take you to the insert GUI and pressing the 'search' button doestake you to the search GUI. | May 27th
III. AI Genre Recognition | 1. Install Deeplearning4j | Friday, April 9th,2021 | 100% | 100% | Can I access the deeplearning4j libraries from Java? Will a program compile if I use a class from deeplearning4j? | I should be able to access the libraries, and the program should compile. | Yes, I can access the libraries and compile files using classes from deeplearning4j.
| 2. Install easy-bert | Friday, April 9th,2021 | 100% | 100% | Can I access the methods in easy-bert to create word vectors from strings? | I should be able to create word embedding vectors from strings like "When mysterious letters start arriving on his doorstep, Harry Potter has never heard of Hogwarts School of Witchcraft and Wizardry." | Yes, I can create word embedding vectors.
| 3. Download the BlurbGenreCollection-EN datasets for training, testing, and validation | Friday, April 9th,2021 | 100% | 100% | N/A | N/A | N/A
| 4. Create a Java preprocessing layer for the data to be used with Deeplearning4j | Friday, April 16th, 2021 | 100% | 100% | Does the preprocessing layer correctly split the dataset into summary & genre, and then spit out the word embedding vectors for each summary? | The preprocessing layer should split the database and spit out embedding vectors. | Yes, the preprocessing layer splits the dataset into blurb and genre and outputs the embedding vectors.
| 5. Use deeplearning4j to create the classification neural net | Friday, April 23rd, 2021 | 100% | 100% | Does the neural net make sense? Why? | The neural net should make sense. I expect the reasoning to be provided in the 'Actual results of test' column. | The neural net makes sense to someone else. I had assumed that this was going to be a simple neural net, but when I did more research, I had discovered that it is more complicated than I had thought. I ended up using a convolutional neural net (whatever that is) based on specifications provided by an academic paper that claimed to have good results on a similar NLP classification task with prebuilt word embedding sets. I, in all honesty, do not understand what the neural net is doing, or why it should work.
| 6. Train the neural net | Monday, May 3rd, 2021 | 100% | 100% | Does the neural net perform with > 80% accuracy on the testing data set? | The neural net should perform with > 80% accuracy on the testing data set. | Alright. So, I'm technically done with these sections, but the neural net is only about 60% accurate, which doesn't match my test. However, I can't really do anything about it. I've tweaked and improved the hyperparameters such that the accuracy rose from 20% to 60%, but I can't get the last 20-25%. This is due to a defect in the BlurbGenreCollection-EN dataset that I describe in the journal entries. Due to copyright/permissions issues, there are very few blurb-genre datasets, and the one I am using is the only one I have found on the internet at all. I've emailed the people who provided the dataset, asking them to fix the defect, but I don't expect to hear back from them.
| 7. Fine tune the neural net's performance with difference optimizers, updaters, initial weights, etc. | Monday, May 3rd, 2021 | 100% | 100% | Does the neural net perform with > 85% accuracy on the testing data set? | The neural net should perform with > 85% accuracy on the testing data set.
| 8. Integrate into the GUI system | Friday, May 7th, 2021 | 100% | 100% | Is the neural net called by the GUI to determine the genre of a book to be inserted? | The neural net should be called by the GUI to determine the genre of each book to be inserted. | The neural net is loaded and the specified blurb is passed through it to return the predicted genre.
IV. Finishing Touches | 1. Package into executable & installer | Friday, May 14th, 2021 | 100% | 60% | Does the generated installer correctly install the executable and necessary files, such that the executable runs the project? | Yes, it should.
V. Presentation | 1. Create presentation | Friday, May 21st, 2021 | 100% | 100% | N/A | N/A | N/A
| 2. Create video | Friday, May 21st, 2021 | 100% | 100% | N/A | N/A | N/A
Notes: I am responsible for the entirety of this project. * = I placed this milestone at the end because I didn't want to have to mess with starting and stopping the database programmatically first; I wanted to write the actual content code and then worry about the small details
Note to self: - remember to write database.properties during installer - write disclaimer and info in main GUI - logging errors
video = demonstration of finished product
presentation = documentation
- initial goals
- struggles
- adjustments necessary
- expected things you learned
- surprising things you learned